Statement of Work · FallEnterprise Tier 4 · AI-Native Enterprise

Engagement value: £200,000+ (from · milestone-billed) · Timeline: 16–20 weeks · 12-month engagement

Between:

- Supplier: AI Native Solutions (Simon Gant, sole practitioner) · United Kingdom

- Client: _________________________________ ("Client")

Effective date: _____________ Contract ref: FE-ENT-YYYY-NNN

1 · Objective

Deliver a full organizational AI transformation. Everything in Tiers 1–3, plus department-by-department rollout, comprehensive staff training programme, 12-month SLA-backed support, and optional custodianship (Supplier operates the stack indefinitely, or Client takes full in-house control at their pace).

The AI becomes operational infrastructure, not a productivity add-on.

2 · Scope of work

2.1 · All of Tiers 1, 2, 3

Everything in Tier 1, Tier 2, and Tier 3. Not repeated.

2.2 · Departmental Rollout Plan (Week 8–10)

- Departmental audit — each business unit's workflows mapped

- AI-integration priority per department (impact × effort matrix)

- Custom workflow design per department (typically 4–8 departments)

- Cross-department integration points identified

- Change management plan (comms, training, rollout order)

2.3 · Departmental Fine-Tuning (Week 10–14)

- Additional fine-tuning rounds — one per department if their workflows are sufficiently distinct

- Alternative: single model with department-specific system prompts + retrieval-augmented context

- Chosen approach based on cost/complexity trade-off with Client input

2.4 · Full Staff Training Programme (Week 10–16)

- Role-based curricula — different training for execs, managers, individual contributors, admin

- Delivery formats — live workshops (on-site or remote), recorded video, written guides

- Certification — competency check per staff member

- Train-the-trainer — 2–5 Client staff certified to train future new hires

Typical volume: 50–500 staff trained during the engagement. Larger orgs scoped separately.

2.5 · SLA-Backed Support (Weeks 16 → 16+52 weeks)

- Response SLA: critical <2h · high <4h · normal <24h (UK business hours)

- Uptime SLA: 99.5% (excluding scheduled maintenance windows)

- On-call rotation for critical incidents

- Monthly review cadence — 60-min call reviewing usage, cost, quality metrics

- Quarterly deep dive — 3-hour on-site (or remote) strategic review

2.6 · Multi-Site Sovereign Network (Week 12–14, optional)

- If Client has multiple locations, configure a sovereign mesh across sites

- Local inference at each site, shared training pipeline centrally

- Fail-over between sites

- Edge deployment for latency-sensitive workflows

2.7 · Custodianship Option (Ongoing)

Client selects at kick-off between:

Option A · Client-operated after handover

- Supplier trains Client's team on full stack operation

- Handover complete at Week 16

- 52 weeks SLA-backed support

- After 52 weeks, Client fully self-sufficient

Option B · Supplier-operated (managed service)

- Supplier retains operational responsibility indefinitely

- Additional cost: £4,000/month post-Week 16 (rolling 12-month contract)

- Includes: monitoring, upgrades, retraining, incident response

- Client can transition to Option A at any point with 60 days' notice

2.8 · Ongoing Retraining (12 months)

- Quarterly retraining runs included (4× over 12 months)

- Data governance reviews quarterly

- Model performance benchmarks quarterly

- Roadmap review at Month 6 and Month 12

3 · Deliverables checklist

| # | Deliverable | Format | Week |
| --- | --- | --- | --- |
| 1–19 | All Tier 1 + 2 + 3 deliverables | (see above SoWs) | 1–12 |
| 20 | Departmental rollout plan | PDF + workshops | 10 |
| 21 | Departmental fine-tunes (as needed) | Models · configs | 14 |
| 22 | Full staff training programme | Recorded + live + certification | 16 |
| 23 | Multi-site config (if applicable) | Deployed + docs | 14 |
| 24 | 12-month SLA + support | Ongoing | 16→16+52w |
| 25 | 4 quarterly retraining runs | Rolling | Month 3, 6, 9, 12 |
| 26 | Custodianship (if selected) | Ongoing operation | Ongoing |

4 · Client responsibilities

In addition to Tiers 1–3:

- Executive sponsor — C-level accountable for the transformation

- Steering committee — meets fortnightly during rollout

- Departmental leads — one per department, empowered to make decisions

- Change management — Client owns internal comms and cultural adoption

- Staff time — allocate training time (typically 8–16 hours per staff member)

5 · Out of scope for Tier 4

Even at the enterprise tier, the following are explicitly out of scope unless separately quoted:

- Enterprise-wide data warehouse redesign

- Replacement of core business systems (ERP, CRM, HRIS)

- Regulatory certification work (SOC 2, ISO 27001) — Supplier provides supporting artifacts but not full certification lead

- More than 1,000 staff members (bespoke scope)

- Custodianship for multiple concurrent Clients on shared infrastructure

6 · Timeline

| Week | Milestone |
| --- | --- |
| 1–2 | Kick-off · executive alignment · discovery |
| 2–5 | Blueprint + Tier 1 ops suite |
| 5–8 | Tier 2 sovereign stack |
| 8–12 | Tier 3 fine-tune + eval |
| 8–10 | Departmental rollout plan |
| 10–14 | Departmental customization + rollout waves |
| 10–16 | Full staff training programme |
| 12–14 | Multi-site (if applicable) |
| 16 | Final handover · SLA period begins |
| 16 → 16+52w | 12-month SLA support · quarterly retrains |

7 · Payment

Milestone-billed. Standard schedule for £200k floor:

- 20% (£40,000) · on signature

- 20% (£40,000) · on Tier 2 sovereign stack live (Week 5)

- 20% (£40,000) · on fine-tune passing eval (Week 9)

- 20% (£40,000) · on departmental rollout complete (Week 14)

- 20% (£40,000) · on final handover (Week 16)

12-month support fee (if Option B custodianship): £48,000 additional, paid quarterly (£12,000 × 4).

Terms: 14 days. Late: 4% above BoE base. Prices exclude VAT.

Larger engagements (>£200k) quoted individually against scope.

8 · Intellectual property

Same as Tier 3, plus:

- All departmental fine-tunes are Client's exclusive property

- Staff training materials delivered as MIT-licensed (Client can modify, reuse, redistribute internally)

- Any tooling built specifically for Client during rollout is Client-owned

- Supplier retains rights to publish generalized case study (with Client's approval, anonymized if requested)

9 · Data & confidentiality

Same as Tier 3, upgraded:

- Comprehensive DPA covering all departments

- Sub-processor list published and updated

- Annual security review with Client

- Right to audit Supplier's security controls annually

10 · Warranties + SLA

- 12-month warranty on all deliverables

- SLA credits for missed uptime targets (5% of monthly support fee per 0.1% below target)

- Response SLA credits for missed response times

11 · Exit & continuity

Same as Tier 3, upgraded:

- Full documentation ensures any competent engineer can take over

- If Option B (custodianship) is selected and Supplier ceases operations mid-contract, Client receives all operational access and 60-day handover support at no additional cost

- Client retains all models, weights, code, data, and configs regardless

12 · Termination

- 60-day notice period for termination for convenience (either party)

- Termination for cause: 30-day cure period after written notice

- If terminated by Client for convenience mid-engagement: pro-rata payment against completed milestones

- Custodianship contract: 60-day notice to cancel, no penalty

13 · Governing law

England & Wales.

Signatures

For the Supplier

Signed: ______________________________  Simon Gant · AI Native Solutions  ·  Date: ____

For the Client

Signed: ______________________________  Print name: ____________________________

Title: ______________________________  Company: ___________________________  ·  Date: ____

Executive sponsor acknowledgement

Signed: ______________________________  Print name: ____________________________

Title: ______________________________  ·  Date: ____

Contract ref: FE-ENT-YYYY-NNN  ·  Version: 1.0  ·  © 2026 AI Native Solutions